## Sheet1
SL NO | TASK | DESCRIPTION | SUBTASK | PROGRESS
1 | Project Initiation and Scope Definition | Review objectives, compliance requirements, and metrics from the scope document. | Scrutinize CSE threat models and artifact requirements. | Pending
|  |  | Outline evaluation criteria and reporting obligations. | Pending
|  |  | Define deliverables, platform tech stack (Docker, Python), | Pending
2 | Solution Architecture and Workflow Design | Design modular architecture for data ingestion, processing, inference, and reporting. | Decide interfaces for crawler, feature extractor, ML models, and reporting. | Pending
|  |  | Design data lake schema, system workflow (crawling → feature extraction → ML inference → alert/report). | Pending
|  |  | Plan infrastructure (on-premises hardware, Docker containers, API endpoints). | Pending
3 | Data Acquisition and Crawler Development | Build systems for continuous crawling, parsing, and acquisition of candidate domains/URLs. | Implement a flexible web crawler with support for tunneling, parked, and lookalike domains. | Pending
|  |  | Integrate screenshot/favicon/image capture. | Pending
|  |  | Schedule crawling cycles, manage seeds and discovered links. | Pending
4 | Feature Engineering | Extract, clean, and structure domain, URL, and artifact features for ML input. | Engineer features listed in annexure A: URL structure, entropy, image similarity, registration/SSL info, etc. | Pending
|  |  | Add advanced features (IDN handling, OCR from images/screenshots, favicon analysis). | Pending
|  |  | Aggregate feature vectors from structured and unstructured data. | Pending
5 | Model Development and Training | Develop and evaluate ML/DL models for phishing/suspected domain classification. | Select algorithms (RF, XGBoost, deep learning ensembles, vision models). | Pending
|  |  | Train and tune models using multiple released datasets. | Pending
|  |  | Validate against benchmarks, hold-out sets, and live data. | Pending
|  |  | Embed explainability/feature importance and continuous learning. | Pending
6 | Automate the process of classifying, scoring, and mapping new URLs/domains in real time. | Set up real-time/batch inference microservice with API endpoints. | Set up real-time/batch inference microservice with API endpoints. | Pending
|  |  | Generate alerts based on scores, CSE mappings, and artifact reports. | Pending
|  |  | Log all results, screenshots, and feature sets per detection. | Pending
7 | Deployment, Dockerization, and QA | Package and QA the system per infrastructure specs. | Dockerize all major components. | Pending
|  |  | Deploy on FIIT/IIT hardware, allocate resources as specified. | Pending
|  |  | Audit and document all dependencies. | Pending
|  |  | Perform stress, functional, and edge-case testing. | Pending